Project Baseline Plan
10-Day Product Development Timeline: Gauge & Grab System
Our Gauge & Grab System helps UCL East users pick the smartest meal option by instantly showing which location offers the fastest service and most appealing menu through a physical colour-coded gauge and a digital twin rich in contextual data.
🟢 Physical Gauge
🔵 Digital Twin
🟣 GitHub & Report
This timeline assumes the 10-day work period runs from Day 1 (December 2nd) to Day 10 (December 11th), with the final Showcase on December 12th.
Day	Date (Approx.)	Phase / Milestone	Key Tasks (Breakdown)	Assigned Team Lead	Necessary Tools/Systems
1	Dec 2nd	Concept & Architecture (M1: System Spec Approved)	1. Define final scope of 3 dining locations (Pool, Marshgate Cafe, Canteen). / 2. Finalise Data Model Schema (EWT, Stock, Score, Weather). / 3. Physical: Select Microcontroller (e.g., ESP32/Arduino) and components (stepper motor for needle, small TFT/E-Ink screen). 4. Digital: Choose Tech Stack (React/Next.js for Twin, Firebase/Firestore for Database).	MD / (Data Lead)	Miro/Figma, Google Sheets, Arduino IDE, Visual Studio Code, Git/GitHub.
2	Dec 3rd	Design & Mockups (M2: High-Fidelity Mockups Complete)	1. Physical: Design 3D model for gauge housing (incorporate needle, screen, 3 buttons, colour zones). / 2. Digital: Create high-fidelity UI/UX mockups for Digital Twin (Attractiveness Chart, Maps, Dialogue). / 3. Data: Build EWT simulation logic (based on time of day, events, etc.) and create mock JSON feed.	ET / (Design Lead)	Figma/Sketch, Fusion 360/Tinkercad, Python (for EWT simulation script).
3	Dec 4th	Hardware Development I (M3: Core Physical Components Wired)	1.Physical: 3D print initial / casing prototype. / 2. Physical: Wire and test microcontroller (MCU) with Wi-Fi/Cloud connection. / 3. Integrate Stepper Motor control for Needle movement (0 to 180 degrees mapping EWT).	YOKB / (Hardware Lead)	Arduino IDE/PlatformIO, Breadboard, Stepper Motor (with driver), Wires, 3D Printer (e.g., UCL workshop).
4	Dec 5th	Data Pipeline Setup (M4: Data Mocking & DB Connection Ready)	1. Data: Set up Firestore database (collections for locations, menu_items, EWT_history, weather). / 2. Data: Write API endpoint (Node.js/Python) to serve mock EWT/Stock/Score data. / 3. Physical: MCU pulls data from the API and successfully prints raw data to the Serial Monitor.	MD / (Data Lead)	Firebase/Firestore, Node.js/Python, Postman (API Testing).
5	Dec 6th	Digital Twin Development I (M5: Core Digital Twin UI Functional)	1. Digital: Set up the main web application framework (React/Next.js) and GitHub Pages deployment environment. 2. Develop the main Dashboard layout, including placeholders for all 3 locations. 3. Integrate Chart.js/Recharts for Menu Attractiveness Chart (hardcoded data initially).	ET (Design Lead)	React/Tailwind CSS, VS Code, Git/GitHub.
6	Dec 7th	Physical Integration I & Twin Data (M6: Physical Gauge EWT Live)	1. Physical: Implement E-Ink/LED display showing the 'top item' status. / 2. Physical: Map EWT values (from live data feed) to the Needle position (0-5 min Green, 5-10 min Yellow, 10+ min Red zones). / 3. Digital: Connect Digital Twin to the Firestore/API data pipeline and display real-time EWT/Stock figures.	MD (Hardware) / ET (Digital)	Arduino C++, React/TypeScript, Firestore SDK.
7	Dec 8th	Feature Development (M7: All Core Features Integrated)	1. Digital: Develop interactive map visualization (simple SVG or Leaflet map showing queue length icons). / 2. Digital: Build the Dialogue Feature placeholder (simple text input/output for personalized recommendations). / 3. Data: Integrate a free Weather API to enrich the data feed (e.g., OpenWeatherMap mock-up).	YOKB (Data) / ET (Digital)	React Components, Weather API, Dialogue/LLM integration (if time allows, otherwise pre-canned responses).
8	Dec 9th	End-to-End Testing & Refinement (M8: System passes E2E Test Scenarios)	1. Testing: Run 10 predefined scenarios (e.g., "7:30 am, heavy rain, low stock at Pool St."). / 2. Physical: Calibrate Needle precision and color mapping under all scenarios. / 3. Digital: Cross-browser compatibility check and mobile responsiveness audit.	All Team Members (Joint)	User Testing Checklist, Browser Developer Tools.
9	Dec 10th	Aesthetics & Showcase Prep (M9: Final Product Polish)	1. Physical: Finalize casing aesthetics, paint, and button labels. Record demonstration videos/photos. / 2. Digital: Apply final visual polish (Tailwind CSS theming, consistent color palette). 3. Documentation: Draft the core content for the GitHub README.md and the 2000-word Report structure (Introduction, Methodology, Results, Conclusion).	YOKB / (Physical) / ET (Digital)	Figma/Design Assets, Video Camera, GitHub.
10	Dec 11th	Finalization & Documentation (M10: Project Documentation Complete)	1. Documentation: Write detailed personal contribution sections for the report. / 2. Final code review and cleanup (add extensive comments). / 3. Deploy final Digital Twin to GitHub Pages using the provided template (https://codepen.io/vsigno/pen/bGJKRYz). / 4. Create the final project presentation slides/script.	All Team Members (Joint)	GitHub, Word Processor/LaTeX (for report).

Group Report (2000 Words, PDF of Readme)
The final 2000-word report, due January 12th, 2026, must follow a formal structure derived from the repository's README.md.
Section	Target Word Count	Key Content & Team Contribution
1. Introduction	200	Project Motivation (UCL East Wait Time Problem), Project Objectives (Gauge & Grab functionality), Scope, and Report Structure.
2. Design & Architecture	400	2.1 Physical Gauge: Hardware selection (MCU, Motor, Display), Casing Design Rationale (MD). / 2.2 Digital Twin: Tech Stack Choice (React, Tailwind), UI/UX Rationale (ET). / 2.3 System Architecture: Data flow diagram (Physical <-> Firestore <-> Digital Twin) (YOKB).
3. Methodology & Development	500	3.1 Data Pipeline: Detailed EWT calculation logic, Data Feeds (Weather, Stock), and Database Structure / 3.2 Physical Prototype Implementation: Code logic for needle movement, color-coding mapping, and button interaction. / 3.3 Digital Twin Implementation: Key features (Attractiveness Chart, Maps), Dialogue feature placeholder (ET).
4. Testing & Validation	300	Results of End-to-End Scenario Testing, Calibration of EWT to Color Zones, User Feedback/Iteration Process.
5. Individual Contributions	400	X: 3D printing, circuit design, MCU coding, physical assembly. / X: Digital Twin UI/UX, Front-end development, visual polish. / X: Data modeling, EWT algorithm, API development, Firestore management.
6. Conclusion & Future Work	200	Summary of success against objectives, challenges encountered (e.g., motor precision, real-time data), and future enhancements (e.g., ML-driven EWT, haptic feedback).

Digital Twin Showcase (December 12th)
The digital component must be hosted on GitHub Pages using the provided template. The focus should be on visualisation and interactivity.
1. Dashboard: Display the color-coded status for all three locations simultaneously, with the main Gauge graphic dominating the screen.
2. Attractiveness Chart: A responsive chart showing Menu Attractiveness (Y-axis) vs. EWT (X-axis) for each location, allowing users to see the trade-off.
3. Real-time Data: Show livestock levels and estimated queue length (as a number of people) updated via the Firestore connection.
4. Dialogue Feature: A simple chat window demonstrating personalized advice, e.g., "Given your history of ordering vegetarian, Pool Street has a Quinoa Salad special today. The EWT is 4 minutes."

Daily Breakdown of Tasks & Milestones
### Day 1: Kickoff & Planning
- Assign roles and responsibilities.
- Sketch gauge concepts
- Wireframe digital twin in Figma
- Define data feeds
### Day 2: Design Phase
- CAD design of gauge in Fusion360
- UI design in Figma/PenPot
- Setup MQTT & REST API feeds
### Day 3: Build Phase Begins
- 3D print gauge housing
- Develop Unity3D twin base
- Integrate data feeds
### Day 4: Hardware & Software Expansion
- Assemble electronics: LED, motor, E-Ink
- Build menu & queue visuals
- Add weather API + menu stock logic
### Day 5: Feature Integration
- Install needle/dial mechanism
- Add personalized recommendation engine
### Day 6: Testing Phase
- Test physical gauge display
- Test digital twin UI
### Day 7: Final Feature Additions
- Integrate gauge with live data feed
- Add E-Ink/LED menu display
- Add real-time map & charts
### Day 8: System Integration Test
Full system test and debugging (All).
### Day 9: Showcase Prep
- Record demo video and take photos (All).
- Compress media using HandBrake/Squoosh
- Write GitHub leaflet using CodePen template
### Day 10: Final Presentation
- Present Gauge & Grab system at UCL East.
- Upload to GitHub Pages.
- Begin drafting 2000-word report for January 12.
## Tools & Platforms Used
- Design: Fusion360, Figma, PenPot, Blender
- Development: Unity3D, ARFoundation, VSCode
- Data Feeds: MQTT (CE Server), REST API
- Assets: Sketchfab (3D), Freesound API (audio)
- Compression: HandBrake, Squoosh
- Documentation: GitHub, CodePen template